FYP Decisions & Execution Plan

Path to August preliminary report — 4-bit quantization safety study

Author: Tan Ue Ihorng (utan001)    Date: 13 May 2026    Target: Preliminary report by 1 Aug 2026

# 1. Executive Summary

You have roughly 11 weeks and an ~8h/week human budget to produce a preliminary FYP report with real cluster results. The code is ready, but no real runs have been executed. The bottleneck is human focus time, not GPU time — cluster jobs run overnight on TC1 while you sleep.

This document captures the ten open decisions, ranks them by urgency, and lays out a week-by-week plan that respects your DBS internship, gym, and the realistic 1-hour weekday evenings + 3–4h Saturday block.

### Headline numbers

- 11 weeks to 1 August (today is 13 May 2026).

- ~8 hours of human focus per week → ~88 hours total.

- 18 cluster jobs to run (6 models × 3 benchmarks). Cluster hours don't burn human hours.

- 10 outstanding decisions. 6 must be locked in Week 1.

- 3 high-urgency risks (refusal regex, Llama access, TC1 walltime OOM).

# 2. Where you are

You sit between phase 5 and phase 6 of a 10-phase project lifecycle. Framework code is complete, test suite passes (119/119), TC1 cluster access and the conda environment are set up, and today's code blockers (4-bit loader, SLURM walltime, sbatch path resolution, squeue scoping, OOM guard) are pushed to GitHub. The next concrete step is a smoke job on TC1.

### Done

- Framework scaffold (benchmark plugins, schema, runners, analyzer, SLURM tooling).

- Local test suite green: 119 tests passing.

- TC1 environment: fyp-tc1 conda env, repo synced, torch + transformers verified.

- Today's blocker fixes committed and pushed to GitHub.

### Next

- Smoke run on TC1 (Qwen 0.8B × HarmBench, n=20).

- First single full job (Qwen 0.8B × HarmBench, n=400).

- Submit the rest of the Qwen pairs.

# 3. Your time budget

A week has 168 hours. FYP is roughly 5% of that. The plan only works if every hour is used for high-leverage work — analysis, writing, decisions — and rote work (running jobs, generating sbatch) is automated or pushed to the cluster.

Cluster hours peak in Weeks 2–4, when the matrix actually runs; human hours peak in Weeks 5–10, when you're writing the report. The two are deliberately offset so neither stage starves the other.

# 4. The ten open decisions

The framework is built, but ten judgment calls remain. Six are scoring / methodology policy. Two are dev-velocity. Two are report-scope. Most flagged by the recent code review are red-urgency: they affect what the headline numbers actually mean.

### At-a-glance table

| ID | Tier | Decision | Recommendation |
| --- | --- | --- | --- |
| D1 | A — lock Week 1 | Refusal-regex breadth | Option (b). ~1h coding + 1h test additions. |
| D2 | A — lock Week 1 | HarmBench scoring policy | Option (b). ~2h to define heuristic + tests. |
| D3 | A — lock Week 1 | MMLU letter parsing | Option (b). ~30min. |
| D4 | A — lock Week 1 | Sample sizes | Option (a) initially; switch to (b) if any job hits walltime in Week 2. |
| D5 | A — lock Week 1 | Llama family inclusion | Option (a) immediately; (b) as fallback by Week 4 if denied. |
| D10 | A — lock Week 1 | Local MPS harness on M2 Mac | Option (b). ~1h. |
| D6 | B — Week 3 | Multi-seed bootstrap CI | Option (c) if time in Week 4-5; (a) otherwise. |
| D8 | B — Week 3 | MMLU subject breakdown | Option (b). ~1h plotting. |
| D7 | C — Week 6+ | Cross-family scope (RQ5) | Decide once Llama access status is known (end of Week 2). |
| D9 | C — Week 6+ | Judge-model refusal grading | Option (a). Out of scope for August preliminary. |

Detail cards for each decision follow on the next pages.

# 5. Decision detail

## Tier A: lock these in Week 1

Tier A decisions all affect the meaning of every number you'll generate. Lock them before the matrix runs, or you'll re-run.

D1  Refusal-regex breadth    HIGH

Question: Should we widen refusal patterns and constrain them to the response prefix?

Why it matters: This regex IS the safety signal. HarmBench ASR and XSTest over-refusal both depend on it. Current patterns miss common Llama-3.2 idioms ("I cannot provide", "I won't", "I'm not able to") and match anywhere in the response, so benign explanations trigger false positives.

Options:

- (a) Keep as-is (status quo, biased toward false negatives on Llama)

- (b) Expand patterns + restrict to first ~120 chars (recommended)

- (c) Replace with LLM judge — adds new dependency

Recommendation: Option (b). ~1h coding + 1h test additions.

Cost: 2h human; 0 GPU    Impact if wrong: High — if wrong, entire HarmBench ASR and XSTest results are biased and the four interpretation labels become unreliable.

D2  HarmBench scoring policy    HIGH

Question: Should off-topic / non-responsive outputs count as harmful compliance?

Why it matters: Current code: anything not a refusal counts as harmful_compliance. A weak model that babbles unrelated text scores as a successful attack, inflating ASR for smaller baselines and confounding the capability_collapse_masquerading_as_safety label.

Options:

- (a) Status quo — binary refusal vs harmful

- (b) Add a third "non-responsive" bucket (recommended)

- (c) Require positive evidence of compliance (e.g. imperative phrasing) — too brittle

Recommendation: Option (b). ~2h to define heuristic + tests.

Cost: 2h human; 0 GPU    Impact if wrong: High — directly affects the interpretation labels which are the headline deliverable.

D3  MMLU letter parsing    MEDIUM

Question: How to extract the model's chosen letter from free-text output?

Why it matters: Current regex matches any A-Z anywhere in the response. "Option A is incorrect; the answer is C" wrongly scores as A.

Options:

- (a) Keep "first letter anywhere"

- (b) Prefer "Answer: X" pattern then fall back to first-letter-on-line (recommended)

- (c) Constrain to last line only

Recommendation: Option (b). ~30min.

Cost: 0.5h human; 0 GPU    Impact if wrong: Medium — adds noise to MMLU accuracy. Doesn't change the qualitative pair-delta direction but widens CIs.

D4  Sample sizes    MEDIUM

Question: Keep 400 / 400 / 300 (HarmBench / XSTest / MMLU) or trim to fit TC1 walltime?

Why it matters: TC1 QoS: MaxWall = 6h, MaxSubmit = 2 concurrent. Qwen 4B at 400 prompts × 128 tokens may approach the wall. Trimming costs statistical power.

Options:

- (a) 400/400/300 as-is (recommended; fall back if needed)

- (b) 200/200/150 — halves cost, doubles CI width

- (c) Tiered: 400 for headline pair, 100 for sensitivity sweeps

Recommendation: Option (a) initially; switch to (b) if any job hits walltime in Week 2.

Cost: Trivial config; affects GPU hours    Impact if wrong: Medium — smaller n widens confidence intervals on deltas. Below ~200 the labels become statistically fragile.

D5  Llama family inclusion    HIGH

Question: Include meta-llama/Llama-3.2-3B-Instruct (gated on HF)?

Why it matters: RQ5 ("Are effects consistent across families?") needs ≥2 families. Llama is the chosen second family but requires HF gated access. Requesting access has lead time.

Options:

- (a) Request HF access on TC1 in Week 1 (recommended)

- (b) Drop Llama; do Qwen-only and kill RQ5

- (c) Substitute another open family (Mistral 7B, Gemma 2B) — needs new sbatch + bnb-4bit checkpoint

Recommendation: Option (a) immediately; (b) as fallback by Week 4 if denied.

Cost: 30min to request; ~0 if denied (configs already exist)    Impact if wrong: High — kills one of five research questions if no second family.

D10  Local MPS harness on M2 Mac    LOW (quick win)

Question: Add Apple Silicon (MPS) support to the loader for local iteration?

Why it matters: Current loader returns CPU on Mac; Qwen 0.8B at 1-3 tok/s makes local smoke tests painful. With MPS at 20-40 tok/s, a 20-prompt smoke runs in ~1 min instead of ~10.

Options:

- (a) Skip — use CPU smoke at --max_samples 5

- (b) Add MPS branch in loader (recommended; 15-line change)

Recommendation: Option (b). ~1h.

Cost: 1h human; 0 GPU    Impact if wrong: Low — pure dev velocity. Does not affect cluster results.

## Tier B: re-evaluate in Week 3

Decide after the smoke and first real runs land — you'll have data to inform the trade-offs.

D6  Multi-seed bootstrap CI    MEDIUM

Question: Run each cell once (seed=42) or repeat with 3 seeds for confidence intervals?

Why it matters: Single-seed greedy decoding is reproducible but a reviewer may flag variance. 3 seeds triples cluster hours.

Options:

- (a) Single seed for all 18 cells (recommended for v1)

- (b) 3 seeds across all 18 cells — 54 jobs, infeasible at 6h walltime each

- (c) Single seed for matrix + 3-seed sensitivity check on Qwen 0.8B only

Recommendation: Option (c) if time in Week 4-5; (a) otherwise.

Cost: Single seed: included. Sensitivity: +3 GPU runs.    Impact if wrong: Medium — affects external credibility, not internal interpretation.

D8  MMLU subject breakdown    LOW

Question: Report aggregate MMLU accuracy only, or per-subject (6 subjects configured)?

Why it matters: Per-subject is richer and may reveal where quantization hurts most, but adds plots and prose. Data is already collected — pure analysis question.

Options:

- (a) Aggregate only — simpler write-up

- (b) Aggregate + flag any subject with delta > 10pp (recommended)

- (c) Full per-subject breakdown for every pair

Recommendation: Option (b). ~1h plotting.

Cost: 1h human; 0 GPU    Impact if wrong: Low-medium — depth vs breadth trade-off in the report.

## Tier C: handle in Week 6+

Scope decisions for the write-up phase, not the running phase.

D7  Cross-family scope (RQ5)    MEDIUM

Question: Commit to RQ5 ("Are effects consistent across families?") in the preliminary report?

Why it matters: Tied to D5. With only Qwen + Llama, RQ5 reduces to a 2-family comparison — defensible but thin. With Qwen only, RQ5 is impossible.

Options:

- (a) Yes if Llama works (recommended)

- (b) Defer RQ5 to the final report

- (c) Drop RQ5 from scope

Recommendation: Decide once Llama access status is known (end of Week 2).

Cost: 0 — scope decision, not a code/run change    Impact if wrong: Medium — changes the scope statement of the report.

D9  Judge-model refusal grading    LOW

Question: Add an LLM judge for refusal classification (v2 enhancement)?

Why it matters: Current v1 uses deterministic regex (explicitly listed as a limitation in docs/limitations.md). A judge model would give a stronger refusal signal but adds another dependency, another sbatch, and another source of variance.

Options:

- (a) Defer to v2 / future work — document as v1 limitation (recommended)

- (b) Add a lightweight judge model (e.g. Llama-Guard) — 4-8h coding + new GPU jobs

Recommendation: Option (a). Out of scope for August preliminary.

Cost: Defer: 0. Add: 6-8h + new sbatch runs.    Impact if wrong: Low for v1 — already framed as a known limitation.

# 6. 11-week execution plan

The plan offsets cluster work (Weeks 2–4, overnight, no human supervision) from writing work (Weeks 5–10, peak human hours). Buffer weeks (W4, W11) are deliberate — internships spike, runs fail, supervisors take leave.

## Weekly breakdown

| Wk | Dates | Focus | Tasks | Hrs |
| --- | --- | --- | --- | --- |
| W1 | 13–19 May | Decisions + Smoke | Lock D1-D3 (scoring policy fixes). 2-3h. Request Llama HF access on TC1 (D5). Add MPS branch to loader (D10). 1h. On TC1: regen sbatch, run smoke (Qwen 0.8B harmbench, n=20). Submit first single full job: Qwen 0.8B × HarmBench, n=400. | 6h |
| W2 | 20–26 May | Qwen matrix | Inspect smoke + single-job summaries; sanity-check refusal / MMLU parsing. Submit all 6 Qwen jobs (0.8B and 4B × 3 benchmarks). Daily 10-min cluster-check before bed. Re-run any failed cells with fixes. | 7h |
| W3 | 27 May – 2 Jun | Llama matrix | Confirm Llama HF access; submit 6 Llama jobs. Run compare_quant_pairs on Qwen-only partial data. Decide D6 (multi-seed sensitivity) and D8 (subject breakdown). | 7h |
| W4 | 3–9 Jun | Buffer + re-runs | Pull cluster results back locally. Re-run any cells with walltime / OOM issues (adjust D4 if needed). Verify all 18 summary.json present. | 6h |
| W5 | 10–16 Jun | Analysis + plots | Final compare_quant_pairs run; commit results. Build headline plots: deltas per benchmark per pair, interpretation-label distribution. Draft Methodology section of the report. | 8h |
| W6 | 17–23 Jun | Results + interpretation | Write Results section: tables, deltas, per-pair labels. Write Discussion: which RQs are supported, which aren't. | 8h |
| W7 | 24–30 Jun | Intro + related work | Write Introduction + research questions (lift from README, expand). Write Related Work (4-bit quantization, safety benchmarks). Write Limitations (D9 belongs here). | 8h |
| W8 | 1–7 Jul | Full draft v1 | Stitch sections; produce v1 PDF. Send to supervisor for early feedback. | 8h |
| W9 | 8–14 Jul | Revise | Address supervisor feedback. Fill gaps; rerun any analysis as requested. | 8h |
| W10 | 15–21 Jul | Polish | Finalize figures; consistent captions; check all references. Proofread; consistency pass. | 8h |
| W11 | 22–28 Jul | Buffer / supervisor review | Final supervisor review. Last-minute fixes. | 4h |
| W12 | 29 Jul – 4 Aug | Submit | Final PDF + submit. | 2h |

# 7. Daily and weekly routine

This is the only routine that survives an internship + gym + 1h weeknight reality. Treat the 20:30–21:30 weeknight block and the Saturday morning block as fixed appointments.

| Time | Activity | Notes |
| --- | --- | --- |
| 07:00 | Wake + commute |  |
| 09:00 – 18:00 | DBS internship | Hard wall — no FYP work. |
| 18:00 – 19:00 | Commute / dinner |  |
| 19:00 – 20:00 | Gym (Mon/Wed/Fri/Sat) | Non-negotiable. Energy buffer for evening focus. |
| 20:30 – 21:30 | FYP focus block (1h) | One small task per evening (e.g. submit 1 job, write 1 paragraph, fix 1 bug). |
| 22:30 | Sleep | Cluster jobs run overnight — wake up to results. |
| Sat AM | FYP deep block (3–4h) | Analysis, writing, plotting — anything needing flow state. |
| Sun | Rest + 1h review | Skim cluster status; plan next week's evening tasks. |

### What 1 hour can actually accomplish (be realistic)

- Submit 1–2 sbatch jobs and verify they land in squeue.

- Read 1 raw.jsonl file end-to-end, sanity-check refusal regex hits.

- Write one paragraph of the report.

- Apply one code fix from the decision list and rerun pytest.

- Generate one plot.

### What requires the Saturday block

- compare_quant_pairs end-to-end + plot generation.

- A full section of the report (methodology, results).

- Debugging anything cluster-side that needs multiple submit-fail-fix cycles.

# 8. Risks and mitigations

### Top three

1. Refusal regex misclassification (high impact × high likelihood). Current patterns miss common Llama refusals and match anywhere in the response. Mitigation: lock D1 in Week 1 before running the matrix.

2. Llama HF access denied (high impact × medium likelihood). Kills RQ5. Mitigation: request access on TC1 in Week 1; if denied by Week 4, drop Llama and rescope to Qwen scale-sensitivity only.

3. TC1 walltime / OOM (medium impact × medium likelihood). Qwen 4B at n=400 may approach the 6h cap. Mitigation: today's matrix runner already releases memory between models via try/finally; if a job still hits walltime, halve max_samples per D4.

### Other mitigations baked into the plan

- Two buffer weeks (W4 and W11) absorb runs that need redo or supervisor delays.

- Pair-level resume (--resume default) means a killed job picks up where it left off.

- Cluster work is async — internship spikes don't block GPU jobs that are already queued.

- Single seed for the headline matrix keeps cluster hours predictable; multi-seed only on the smallest pair if time.

# 9. Concrete actions this week

Six things to get through Week 1 (13–19 May). Treat them as a checklist.

- Mon evening: Lock D1 — expand refusal regex and restrict to response prefix. Push fix + tests.

- Tue evening: Lock D2 — add "non-responsive" bucket to HarmBench scoring. Push fix + tests.

- Wed evening: Lock D3 — "Answer: X" preference in MMLU parser. Push fix + tests.

- Thu evening: On TC1: git pull, pip install -r requirements.txt (picks up bitsandbytes + accelerate), regenerate sbatch with the new walltime/path fixes, submit smoke.

- Fri evening (or skip if gym): Request Llama HF access. Add D10 MPS branch to loader if energy permits.

- Sat morning (3–4h): Submit Qwen 0.8B × HarmBench full job (n=400). While it runs, draft your week-2 sbatch submission plan.

# 10. References

All linked files are in the repo at github.com/tanueihorng/llm-ethics-benchmark.

- CLAUDE.md — repo conventions for future agent sessions.

- docs/TC1_CLUSTER_RUNBOOK.md — step-by-step TC1 operational guide.

- docs/methodology.md — research methodology.

- docs/limitations.md — known v1 limitations (where D9 lives).

- ethical_benchmark/analysis/compare_quant_pairs.py — pair-delta + interpretation labels.

- configs/tc1.yaml — TC1 SLURM config (work_dir, partition, walltime).

- Pull request review (in chat history) — full list of blockers fixed and should-fix items still open.